## Enunciado
Planificación SCRUM
Cliente (Product Manager):
-aplicación cliente /servidor
-pantalla autenticación de usuario
-Base de datos de usuarios
-Envio de facturas entre cliente y servidor
-Interfaz Web de administración de usuarios
-Interfaz de Escritorio para los programas cliente y servidor
-Interfaz de servidor de Escritorio: usuarios conectados
-Facturas: c (texto)--->s (PDF) en base de datos
2 programadores
Sprint Backlog
x5

## Product Backlog
Product Backlog
| Organización | EHU - EUI
| Proyecto | Práctica de Scrum - ADSI
| Scrum Master | Nombre de Alumno
| Product Owner | Mari Carmen Otero
Story ID | Nombre | User story | Priority | Sprint #
1 | Autenticar usuario | Como usuario, necesito autenticarme para acceder al sistema. | 2 | 1
2 | Registrar usuario | Como usuario necesito registrarme para luego poder autenticarme. | 1 | 1
3 | Gestionar usuarios | Como usuario, puedo modificar y añadir datos a mi cuenta. | 4 | 2
4 | Registrar alojamiento | Como usuario, puedo poner un alojamiento en alquiler. | 3 | 1
5 | Modificar alojamiento | Como arrendador, puedo modificar la información de mi alojamiento (tipo de propiedad, nº huespedes, dormitorios, barrio...) | 5 | 2
6 | Buscar alojamiento | Como usuario arrendatario, puedo buscar un local para alquilar. | 6 | 2
7 | Alquilar alojamiento | Como usuario, puedo alquilar un alojamiento. | 7 | 3
8 | Realizar pago | Como arrendatario, debo introducir mis datos de pago. | 8 | 3
9 | Cancelar alquiler | Como usuario, tanto arrendador como arrendatario, puedo cancelar un alquiler | 9 | 3
Note on A10: A unique ID to refer to this story. Doesn't have to be numeric.
Note on B10: A short title just enough to recall the story.
Note on C10: (from product owner) Description of the user story in common language. Keep it short (one or wo sentences). Usually formatted as: "As a <role> I want to <function> so that <benefit>".
Note on D10: (from product owner) Priority of this story. Use an open scale so you can always move priorities later.
Note on E10: Fill in after Sprint Planning Meeting

## Sprint 1
Sprint #1Tracking Sheet
[14 empty] | 0 | 34
|  | Proyecto | Práctica de Scrum - ADSI | [10 empty] | 8 | 0
|  | Scrum Master | Nombre de Alumno (a rellenar)
|  | Sprint # | 1
|  | Fecha inicio | 2015-11-16
|  | Días | 8
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Tarea ID | Story ID | Descripción | Estimación | 2015-11-16 | 2015-11-17 | 2015-11-18 | 2015-11-19 | 2015-11-20 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27
1 | 1 | Instalar, configurar MySQL y crear la BD de usuarios | 6 | 2015-11-16: 4
2 | 1 | Diseño de la interfaz de autenticación | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5
3 | 1 | Autenticación | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
4 | 1 | Perdí mi contraseña | 6 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0
5 | 1 | Control de sesión en la web | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0
|  | Remaining units (actual) | 34 | 28 | 24 | 24 | 20 | 14 | 12 | 10 | 5 | 0 | 0
|  | Remaining units (ideal) |  | 29.75 | 25.5 | 21.25 | 17 | 12.75 | 8.5 | 4.25 | 0 | 0 | 0
Note on D6: Olivier Gérardin: The sprint number.
Note on D7: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on M11: MariCarmen: A partir del 26/11 se defienden los trabajos de HTML5, CSS y JS.
Note on A12: Olivier Gérardin: A unique Task ID
Note on B12: Olivier Gérardin: The Story this task will help complete.
Note on D12: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E12: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C21: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D21: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C22: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.

## Sprint 2
Sprint #2Tracking Sheet
[14 empty] | 0 | 34
|  | Proyecto | Práctica de Scrum - ADSI | [10 empty] | 8 | 0
|  | Scrum Master | Nombre de Alumno (a rellenar)
|  | Sprint # | 2
|  | Fecha inicio | 2015-12-14
|  | Días | 8
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Tarea ID | Story ID | Descripción | Estimación | 2015-12-14 | 2015-12-15 | 2015-12-16 | 2015-12-17 | 2015-12-18 | 2015-12-21 | 2015-12-22 | 2015-12-23 | 2015-12-24 | 2015-12-25
1 | 2 | Descripción 1 | 6 | 2015-12-14: 4
2 | 2 | xx | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5
3 | 3 | xx | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
4 | 3 | xx | 6 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0
5 | 2 | xx | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0
|  | Remaining units (actual) | 34 | 28 | 24 | 24 | 20 | 14 | 12 | 10 | 5 | 0 | 0
|  | Remaining units (ideal) |  | 29.75 | 25.5 | 21.25 | 17 | 12.75 | 8.5 | 4.25 | 0 | 0 | 0
Note on D6: Olivier Gérardin: The sprint number.
Note on D7: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on M11: MariCarmen: No se trabaja, es visperas de Navidad.
Note on A12: Olivier Gérardin: A unique Task ID
Note on B12: Olivier Gérardin: The Story this task will help complete.
Note on D12: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E12: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C21: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D21: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C22: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.

## Sprint 3
Sprint #3Tracking Sheet
[14 empty] | 0 | 34
|  | Proyecto | Práctica de Scrum - ADSI | [10 empty] | 8 | 0
|  | Scrum Master | Nombre de Alumno (a rellenar)
|  | Sprint # | 3
|  | Fecha inicio | 2015-12-28
|  | Días | 8
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Tarea ID | Story ID | Descripción | Estimación | 2015-12-28 | 2015-12-29 | 2015-12-30 | 2015-12-31 | 2016-01-01 | 2016-01-04 | 2016-01-05 | 2016-01-06 | 2016-01-07 | 2016-01-08
1 | 4 | Descripción 12 | 6 | 2015-12-28: 4
2 | 4 | xx | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5
3 | 5 | xx | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
4 | 6 | xx | 6 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0
5 | 6 | xx | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0
|  | Remaining units (actual) | 34 | 28 | 24 | 24 | 20 | 14 | 12 | 10 | 5 | 0 | 0
|  | Remaining units (ideal) |  | 29.75 | 25.5 | 21.25 | 17 | 12.75 | 8.5 | 4.25 | 0 | 0 | 0
Note on D6: Olivier Gérardin: The sprint number.
Note on D7: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on M11: MariCarmen: Es la entrega de la práctica de EuskalRent o EuskalLove
Note on A12: Olivier Gérardin: A unique Task ID
Note on B12: Olivier Gérardin: The Story this task will help complete.
Note on D12: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E12: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C21: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D21: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C22: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.